## Folha1
KO |  | KO+2 |  |  |  | KO+6 |  | KO+8 |  |  |  | KO+ 12 | KO+ 13 | KO+ 14
Semanas | #1 | #2 | #3 | #4 | #5 | #6 | #7 | #8 | #9 | #10 | #11 | #12 | #13 | #14
Deliverables
Vision & Scope | bar: #1 to KO+2 #2
Milestone Report 1.1 | KO+2 #2: R/B
Software Development Plan | bar: KO+2 #3 to KO+6 #6
Quality Assurance Plan | bar: KO+2 #4 to KO+6 #6
Milestone Report 1.2 | KO+6 #6: R/B
Software Requirements Specification | bar: KO+6 #7 to KO+8 #8
Risk Plan | bar: KO+6 #7 to KO+8 #8
Acceptance Test Plan | bar: KO+6 #7 to KO+8 #8
Milestone Report 2.1 | KO+8 #8: R/B
Software Architecture & Design | bar: KO+8 #9 to KO+ 12 #12
Milestone Report 2.2 | KO+8 #9: R; KO+8 #10: R; KO+8 #11: R; KO+ 12 #12: R/B
Acceptance Test Report | bar: KO+ 13 #13
Quality Assessment Report | bar: KO+ 13 #13
Milestone Report 2.3 | KO+ 14 #14: R/B
Post-Mortem Analysis | bar: KO+ 14 #14
Legenda: | KO+2 #3: ¦ - Milestone; KO+6 #6: S - Semana; KO+8 #9: R - Review; KO+ 12 #12: B - Baseline