## Gantt
GPS 2019/2020 Bill Splitter Earned Value Analysis |  |  | Budgeted Cost of Work (BCW) |  |  |  |  | Actual Cost of Work (ACW) |  |  |  | Earned Value Analysis | Calendar (weeks)
| Baselined schedule |  | Planned start | Planned complete | Start from previous start | Planned duration (weeks) | Estimated effort (hours) | Actual start | Actual complete | Actual effort (hours) | Actual value (hours) |  | 2019-10-30 | 2019-11-06 | 2019-11-13 | 2019-11-20 | 2019-11-27 | 2019-12-04 | 2019-12-11 | 2019-12-18
[13 empty] | 30-10-2019 | 06-11-2019 | 13-11-2019 | 20-11-2019 | 27-11-2019 | 04-12-2019 | 11-12-2019 | 18-12-2019 | 30-12-1899 | 30-12-1899 | 30-12-1899 | 30-12-1899 | 30-12-1899 | 30-12-1899
| Baseline 1 - KOM | 2019-10-31 | 2019-10-30 | 2019-12-18 | 0 | 7 | 112 |  |  |  |  | Budget at Completion (BAC) | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112
[12 empty] | Planned Value (PV) | 0 | 8 | 15 | 26 | 45 | 71 | 95 | 111
[12 empty] | Earned Value (EV) | 0 | 3 | 3 | 14 | 34 | 71 | 87 | 103
WBS | Live values |  | 2019-10-30 | 2019-12-18 |  | 7 | 111 | 2019-10-30 | 2019-11-06 | 115 | 103 | Actual Cost (AC) | 0 | 14 | 33 | 49 | 66 | 81 | 100 | 115
Stage | Task | Subtask | [9 empty] | Notes | 2019-10-30: Actual work expended (Mark with X when task completed)
2.1. SW Requirements Specification | D2.1.1 Software Requirements Specification |  | 2019-10-30 | 2019-11-06 |  | 1 | 8 | 2019-10-30 | 2019-11-20 | 27 | 8 |  | 10.5 | 15.5 | 1 | x | x | x | x | x | x | x | x | x | x | x
2.1. SW Requirements Specification | D2.1.2 Risk Plan |  | 2019-10-30 | 2019-11-13 | 0 | 2 | 3 | 2019-10-30 | 2019-11-06 | 2 | 3 |  | 2 | x | x | x | x | x | x | x | x | x | x | x | x | x
2.1. SW Requirements Specification | D2.1.3 Acceptance Test Plan |  | 2019-10-30 | 2019-11-13 | 0 | 2 | 3 | 2019-10-30 | 2019-11-27 | 8 | 3 |  | 1.5 | 3.5 |  | 3 | x | x | x | x | x | x | x | x | x | x
2.1. SW Requirements Specification | D2.2.1 Software Architecture & Design |  | 2019-10-30 | 2019-12-11 | 0 | 6 | 8 | 2019-11-13 | 2019-12-04 | 3.5 | 8 |  |  |  | 3 |  | 0.5 | x | x | x | x | x | x | x | x | x
2.1. SW Requirements Specification | D2.1.4 Milestone Report 2.1 |  | 2019-11-06 | 2019-11-13 | 1 | 1 | 1 | 2019-11-13 | 2019-11-27 | 2.5 | 1 |  |  |  | 2 | 0.5 | x | x | x | x | x | x | x | x | x | x
2.2. SW Development | Desenvolvimento do código fonte da lógica | Teste Unitário | 2019-11-13 | 2019-12-04 | 1 | 3 | 13 | 2019-11-13 | 2019-12-04 | 10.5 | 13 |  |  |  | 2 | 4 | 4.5 | x | x | x | x | x | x | x | x | x
2.2. SW Development | Envio da informação do evento para o servidor | Teste Unitário | 2019-11-13 | 2019-11-27 | 0 | 2 | 13 | 2019-11-13 | 2019-12-04 | 6.5 | 13 |  |  |  | 1.5 |  | 5 | x | x | x | x | x | x | x | x | x
2.2. SW Development | Envio da informação do evento para o cliente | Teste Unitário | 2019-11-20 | 2019-12-04 | 1 | 2 | 8 | 2019-11-20 | 2019-11-27 | 4.5 | 8 |  |  |  |  | 4.5 | x | x | x | x | x | x | x | x | x | x
2.2. SW Development | Lista de eventos | Teste Unitário | 2019-11-20 | 2019-11-27 | 0 | 1 | 3 | 2019-11-20 | 2019-11-27 | 3 | 3 |  |  |  |  | 3 | x | x | x | x | x | x | x | x | x | x
2.2. SW Development | Ver evento | Teste Unitário | 2019-11-13 | 2019-11-20 | -1 | 1 | 3 | 2019-11-27 | 2019-12-04 | 4 | 3 |  | 2019-11-27: 4; 2019-12-04: x; 2019-12-11: x; 2019-12-18: x | x | x | x | x | x | x
2.2. SW Development | Criação de eventos | Teste Unitário | 2019-11-13 | 2019-11-20 | 0 | 1 | 5 | 2019-11-13 | 2019-11-27 | 4.5 | 5 |  |  |  | 2.5 | 2 | x | x | x | x | x | x | x | x | x | x
2.2. SW Development | Editar eventos | Teste Unitário | 2019-11-20 | 2019-11-27 | 1 | 1 | 3 | 2019-11-27 | 2019-12-11 | 4 | 3 |  | 2019-11-27: 1; 2019-12-04: 3; 2019-12-11: x; 2019-12-18: x | x | x | x | x | x | x
2.2. SW Development | Autenticação | Teste Unitário | 2019-11-13 | 2019-11-20 | -1 | 1 | 3 | 2019-11-13 | 2019-11-20 | 4 | 3 |  |  |  | 4 | x | x | x | x | x | x | x | x | x | x | x
2.2. SW Development | Partilha de evento | Teste Unitário | 2019-11-27 | 2019-12-04 | 2 | 1 | 5 | 2019-12-04 | 2019-12-18 | 4 | 5 |  | 2019-12-04: 1; 2019-12-11: 3; 2019-12-18: x | x | x | x | x | x | x
2.2. SW Development | Walkthroughs |  | 2019-11-20 | 2019-12-11 | -1 | 3 | 5 | 2019-12-04 | 2019-12-11 | 5 | 5 |  | 2019-12-04: 5; 2019-12-11: x; 2019-12-18: x | x | x | x | x | x | x
2.2. SW Development | Desk Checks |  | 2019-11-20 | 2019-12-11 | 0 | 3 | 8 | 2019-12-04 | 2019-12-11 | 7 | 8 |  | 2019-12-04: 7; 2019-12-11: x; 2019-12-18: x | x | x | x | x | x | x
2.2. SW Development | Teste de integração |  | 2019-11-27 | 2019-12-18 | 1 | 3 | 8 | 2019-12-11 |  | 4 | 0 |  | 2019-12-11: 4
2.2. SW Development | Teste de aceitação |  | 2019-12-11 | 2019-12-18 | 2 | 1 | 1 | 2019-12-11 | 2019-12-11 | 0.5 | 1 |  | 2019-12-11: 0.5; 2019-12-18: x | x | x | x | x | x | x
2.2. SW Development | D2.2.2 Milestone Report 2.2 |  | 2019-12-04 | 2019-12-11 | -1 | 1 | 3 | 2019-12-04 | 2019-12-11 | 3.5 | 3 |  | 2019-12-04: 3; 2019-12-11: 0.5; 2019-12-18: x | x | x | x | x | x | x
2.3. SW Acceptance and Delivery | D2.3.1 Acceptance Test Report |  | 2019-12-11 | 2019-12-18 | 1 | 1 | 3 | 2019-12-11 | 2019-12-11 | 3 | 3 |  | 2019-12-11: 3; 2019-12-18: x | x | x | x | x | x | x
2.3. SW Acceptance and Delivery | D2.3.2 Quality Assessment Report |  | 2019-11-13 | 2019-12-18 | -3 | 5 | 3 | 2019-12-11 | 2019-12-11 | 3 | 3 |  | 2019-12-11: 3; 2019-12-18: x | x | x | x | x | x | x
2.3. SW Acceptance and Delivery | D2.3.3 Milestone Report 2.3 |  | 2019-12-11 | 2019-12-18 | 4 | 1 | 1 | 2019-12-11 | 2019-12-11 | 1 | 1 | [9 empty] | x | x | x | x | x | x | bar: 2019-12-11 to 2019-12-18
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
Formulas:
Budgeted Cost of Work (BCW) = IF(OR(ISBLANK(N2),ISBLANK([Stage])),"",OFFSET(N2,0,F10+MATCH([Budgeted Cost of Work (BCW), row above],N2:AA2,0)-1))
Budgeted Cost of Work (BCW) = IF(OR(ISBLANK(N2),ISBLANK([Stage])),"",OFFSET(N2,0,F12+MATCH(D10,N2:AA2,0)-1))
Actual Cost of Work (ACW) = iferror(index(N2:AA2,1,match(1,if(isnumber([Calendar (weeks)]:AA9),1,0),0)))

## Tables
Stage
2.1. SW Requirements Specification
2.2. SW Development
2.3. SW Acceptance and Delivery